## Q1
Week | Source control | CI | CD | Create documentation | Difficulty (1-easy, 3-hard)
2020-10-01 | Get familiar with git |  |  |  | 2
2020-10-08 | Set up git | Get familiar with Azure Cloud Shell |  | Create README file | 2
2020-10-15 | Create GitHub Repo | Set up Azure Cloud Shell |  |  | 1
2020-10-22 |  | Configure GitHub Actions |  |  | 1
2020-10-29 |  |  | Set up Azure Pipelines |  | 3
2020-11-05 |  |  |  | Update README file | 1
2020-11-12 |  |  |  | Demo work | 2
2020-11-19
2020-11-26
2020-12-03 | Ready for QA | Ready for QA | Ready for QA
2020-12-10
2020-12-17
| Goals | Goals | Goals | Goals
| Modify and automate changes | Check and automate code | Automate delivery | Effective technical communication